## Shop
UNIT | JOB | TYPE | FREQUENCY | STATUS | MECHANIC | LOCATION | START | DUE | COMPLETED | PRIORITY | NOTES
ALL VANS | Pre-trip wash & disinfect stalls | ROUTINE | DAILY |  | Luis |  |  | 2026-09-26
FLEET | Tire pressure & tread check | ROUTINE | WEEKLY | DONE | Mike |  |  | 2026-09-28 | 2026-09-25
TRAILERS | Floor mat & ramp inspection | ROUTINE | MONTHLY |  |  |  |  | 2026-09-24 |  |  | Check ramp springs on 40-series
VAN 112 | Brake job - rear axle | ONGOING |  | IN PROGRESS | Mike |  | 2026-09-24 | 2026-09-27 |  | HIGH
VAN 118 | A/C compressor replacement | ONGOING |  | WAITING ON PARTS | Luis | In house | 2026-09-21 | 2026-09-25 |  |  | Compressor ETA Tue
TRL 44 | Divider latch repair | ONGOING |  | IN PROGRESS | Ray |  | 2026-09-26 | 2026-09-26
VAN 105 | Oil change & filters | ONGOING |  | DONE | Ray |  | 2026-09-26 | 2026-09-26 | 2026-09-26
VAN 121 | Annual DOT inspection | SCHEDULED |  |  | Mike |  | 2026-09-28 | 2026-09-28 |  | HIGH
VAN 109 | PM service - 25k | SCHEDULED |  |  |  |  | 2026-09-27
TRL 38 | Wheel bearing repack | SCHEDULED |  |  | Ray |  | 2026-10-02
VAN 114 | Generator service | SCHEDULED |  |  |  | Cummins | 2026-10-06 |  |  |  | Book with Cummins